## Product Backlog
[11 empty] | Level | Priority |  |  |  | Estimate
[11 empty] | 1 | High |  |  |  | Estimated time to complete the work (hour)
[11 empty] | 2 | Medium
[11 empty] | 3 | Low
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Login | User, Shipper, Admin | access to the Application by my account | I can use the Application with my role. | User can login into system when they input correctly Email value, Password value and log in. - Generate failure or success messages when processing. - Show the error messages when value is invalid. |  | 1 |  |  |  | 1~2~3 | 20
PB02 | Logout | User, Shipper, Admin | logout of the system | I can stop using the system. | User log out of the system when User click the icon logout |  | 3 |  |  |  | 1~2~3 | 32
PB03 | Register | Users | create my account | I can use that account to login the system. | User can create new account by entering Username, Password and Email: - Email must exist. - Enter Email in correct format. - Email does not include special characters, spaces. - Password has no spaces. - Generate error or success message when processing. - Display an error message when the value is invalid. |  | 1 |  |  |  | 1 | 36
PB04 | Forgot Password | Users | retrieve my password | I can access my account. | - When the user presses the [Forgot Password] button at the login screen. - User enters new password provided at Mobile Phone. - Login to the homepage to be able to change the password that the user wants. - Generate error or success message during processing. - Display an error message when the value is invalid. |  | 1 |  |  |  | 1 | 21
PB05 | Change Password | User, Shipper | change my password | i can make my account better secured | - User clicks [Change password] button, the system will go to the change password page - User will enter the old password, new password and re-enter the new password + Then click [Save] button + If the user enters the correct old password, it is allowed to change the password - If the old password is wrong, display the message [Old password is incorrect] and do not change the password |  | 2 |  |  |  | 1~3 | 18
PB06 | View history | User, Shipper | view a order history | i can see what i bought on the app | The user clicks on the store icon to view the corresponding history. Here you can view your order history. |  | 2 |  |  |  | 1~3 | 45
PB07 | View notification | User | See announcements from the facility | I can receive facility updates and view announcements. | User click icon notification button. |  | 2 |  |  |  | 1 | 13
PB08 | Add address | User | add my address to the app | the app can be delivered food to me | - User clicks [Add Address] - Tap the plus sign to add an address - Press the [Save] button to finish changing the information. - Press the back button to cancel the function. |  | 2 |  |  |  | 1 | 8
PB09 | Suggest Food | User | I want food suggestions if I don't know what to buy | I can Acess the application and chosse food suggestions | - Every time the user logs into their application, the application will present to the user the interface Suggested food according to each type of dish (savoury, vegetarian, sweet), diet for the user. - If they don't want suggestions, they can click on the words "self-selected food"
PB10 | Purchase, Online Payment | User | Buy food and Online payment from establishments via the app | it can be convenient for me. | - User clicks on the app's icon on the main page - Then click Order - The user adds the product to the cart and takes the next steps to place an order - After completing the system will send the order to the store |  | 2 |  |  |  | 1 | 10
PB11 | Accept order | Shipper | Receive orders from users | I can take orders from customers and start buying them what they need | - The shipper can receive information from the orderer - Click [Accept] to confirm the delivery order |  | 3 |  |  |  | 3 | 12
PB12 | Check Information | Admin | See the Ìnformation | I can acess to system and manage . | - The administrator selects one from the information management list (Account, order). - Show detailed information about it. |  | 1 |  |  |  | 2 | 12
PB13 | Show dashboard | Admin | show a dashboard | I can improve the system's productivity. | - Admin clicks [Show Dashboard]. Show detailed information. |  | 1 |  |  |  | 2 | 15
PB14 | Give warnings | Admin | send alerts, news to end users | I can see and avoid them. | - Admin clicks [Message], the system will switch to a page that allows Admin to add notifications to users - If [Cancel] is pressed, the function will stop. - If [Submit] is clicked, an alert or news will be sent to the user. |  | 1 |  |  |  | 2 | 10
PB15 | Manage accounts | Admin | Manage shipper accounts | I can CRUD shipper accounts | - Admin clicks [Shipper Account], the system will switch to a page allowing Admin to view Shipper information - If [Cancel] is pressed, the function will stop. |  | 1 |  |  |  | 2 | 15
PB16 | See user feedback | Admin | Check feedback about product | I can Acess to feedback in dashboard and See all feedback from User | - Admin clicks [Customer Feedback], the system will switch to a page that allows Admin to view feedback content - If [Cancel] is pressed, the function will stop. - If [Send] is clicked, a response will be sent to the user. |  | 2 |  |  |  | 2 | 10
PB17 | View Cart | User | Have a shopping cart to buy multiple products at once | I can Add product to cart and check out | - User click [ My Cart ], the system will switch to a page allow User view added product in cart |  | 2 |  |  |  | 1 | 20
PB18 | Feedback | User | Write a Feedback about delivery service or product quality | I can feedback after I pay and product received my order | - After Users pay and received order, they can click on feedback button and write feedback to Admin |  | 3 |  |  |  | 1 | 12
PB19 | Tracking Delivery time | User | Know when my product will be delivered | I can see what time the delivery person will arrive | - After Confirm order User will get receive a notification about the delivery time |  | 2 |  |  |  | 1 | 15
PB20 | View infomation about Customer order | Shipper | Know the customer's phone number and address | I can deliver to the user | - After receive order from User Shipper shipper can click on that order and see information about who order |  | 2 |  |  |  | 3 | 12
PB21 | Change personal information | User, Shipper | Change my personal Infomation | I can change the personal ìnormation in the application | User And Shipper have a tab Called "Profile" and they can change all information personal in this tab |  | 3 |  |  |  | 1~3 | 10

## Main (hidden)
Project | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2023-03-15 | 2023-04-12 | Complete | 21 | 21
[6 empty] | 2 | 2023-04-13 | 2023-05-01 | Complete | 21 | 20
[6 empty] | 3 | 2023-05-02 | 2023-05-22 | Complete | 21 | 23
Formulas:
Project #1 = [Start]+28
Start = [Project #1, row above]+1

## Sprint 1 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint |  |  |  |  | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated
[7 empty] | Remaining work to be done. | Total number of hours you spent on the task. Your effort
[10 empty] | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
1.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 3 | Ahead Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 |  | Create Sprint backlog | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | Create Test Plan document | All members | Done | 6 | 6 | 0 | 5 | Ahead Schedule | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 |  | Create Database document | All members | Done | 6 | 6 | 0 | 6 | On Schedule | 0 |  | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | PB14 | Create UserInterface document | Phuc, QNhat | Done | 1 | 1 | 0 | 0.5 | Ahead Schedule | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | PB01 | Design UI for user to Login | Thai | Done | 1 | 1 | 0 | 0.5 | Ahead Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | PB03 | Design UI for user to Register | Phuc | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | PB04 | Design UI for user to Forgot password | Thai | Done | 0.5 | 0.5 | 0 | 0.5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 |  | Design UI for user to Enter the main homepage | QNhat | Done | 0.5 | 0.5 | 0 | 0.5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | PB05 | Design UI for user to Change password | Thai | Done | 1 | 1 | 0 | 0.5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.11 | PB10 | Design UI for user to Edit Profile | QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.12 | PB18 | Design UI for user to View Cart | Phuc | Done | 1 | 1 | 0 | 0.5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.13 | PB16 | Design UI for user to Order | QNhat | Done | 0.5 | 0.5 | 0 | 0.5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.14 | PB20 | Design UI for user to see delivery time | QNhat | Done | 0.5 | 0.5 | 0 | 0.5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.15 | PB09 | Design UI for user Food Suggest | Nhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.16 | PB19 | Design UI for user Feedback | Thai, Nhat | Done | 1 | 1 | 0 | 0.5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.17 | PB10 | Design UI for user to Online Payment | Nhat | Done | 2 | 2 | 0 | 0.5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.18 | PB14 | Design UI for View history order | Nhat | Done | 2 | 2 | 0 | 1 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.19 |  | Design Test case | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | PB01 | Code Frontend for user to Login | Thai | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.21 | PB03 | Code Frontend for user to Register | Phuc | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.22 | PB04 | Code Frontend for user to Forgot password | Thai | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.23 |  | Code Frontend for user to Enter the main homepage | QNhat | Done | 3 | 3 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.24 | PB05 | Code Frontend for user to Change password | Thai | Done | 4 | 4 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.25 | PB10 | Code Frontend for user to Edit Profile | Thai | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.26 | PB14 | Code Frontend for user to View Cart | Phuc | Done | 5 | 5 | 0 | 6 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.27 | PB20 | Code Frontend for to see delivery time | QNhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.28 | PB15 | Code Frontend for Suggest Food | Nhat, Thai | Done | 6 | 6 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.29 | PB19 | Code Frontend for user Feedback | Nhat | Unfinish | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | PB16 | Code Frontend for user to Order | Nhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.31 | PB10 | Code Frontend for user Online Payment | Nhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.32 | PB14 | Code Frontend for user View history order | Phuc | Unfinish | 2 | 2 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.33 | PB01 | Code Backend for user to Login | Thai | Done | 3 | 3 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.34 | PB03 | Code Backend for user to Register | Phuc | Done | 3 | 3 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.35 | PB04 | Code Backend for user to Forgot password | Nhat | Done | 4 | 4 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.36 | PB10 | Code Backend for user to Edit profile | Thai | Done | 4 | 4 | 0 | 1 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.37 | PB18 | Code Backend for user to View Cart | Thai | Done | 4 | 4 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.38 | PB19 | Code Backend for user to Feedback | Phuc | Unfinish | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1.39 | PB16 | Code Backend for user to Order | Thai | Done | 4 | 4 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | PB14 | Code Backend for user to View history order | QNhat | Unfinish | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
1.41 | PB10 | Code Backend for user to Online Payment | Thai | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
1.42 | PB20 | Code Backend for user to See delivery time | QNhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
1.43 | PB10 | Code Backend for user to Food Suggest | Thai | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
1.44 | PB05 | Code Backend for user to Change password | Nhat | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
1.45 |  | Testing | All members | Done | 5 | 5 | 0 | 4 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0
1.46 |  | Fix bug | All members | Done | 4 | 4 | 0 | 6 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1.47 |  | Re-Testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1.48 |  | Sprint 1 Review Meeting | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
1.49 |  | Release Sprint 1 | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Total | 153 | 153 | 0 | 135 |  | 4 | 8 | 6 | 3 | 1 | 2 | 3.5 | 4.5 | 6 | 4 | 3 | 3 | 5 | 10 | 9 | 7 | 8 | 5 | 7 | 4 | 4 | 7 | 3 | 8 | 4 | 11 | 8 | 5
|  |  |  | Burn down | [5 empty] | 149 | 141 | 135 | 132 | 131 | 129 | 125.5 | 121 | 115 | 111 | 108 | 105 | 100 | 90 | 81 | 74 | 66 | 61 | 54 | 50 | 46 | 39 | 36 | 28 | 24 | 13 | 5 | 0
|  |  |  | Burn up | [5 empty] | 4 | 12 | 18 | 21 | 22 | 24 | 27.5 | 32 | 38 | 42 | 45 | 48 | 53 | 63 | 72 | 79 | 87 | 92 | 99 | 103 | 107 | 114 | 117 | 125 | 129 | 140 | 148 | 153
[5 empty] | Member | Estimate
[5 empty] | Thai, Bui Son | 51.25
[5 empty] | Nhat, Nguyen The | 34.75
[5 empty] | Phuc, Dang Hong | 29.75
[5 empty] | Nhat, Dao Quang | 28.25
[5 empty] | Total | 144

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Sprint Backlog
[10 empty] | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18
2.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 |  | Create Sprint backlog for Sprint 2 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 |  | Create Test Plan document for Sprint 2 | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 |  | Create Database document for Sprint 2 | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | PB01 | Design UI for the admin to Login | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7 | PB02 | Design UI for the admin to Logout | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.8 | PB15 | Design UI for Contact the Admin Check Information | Phuc, QNhat | Done | 2 | 2 | 0 | 1 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.9 | PB15 | Design UI for Admin to Show dashboard | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | PB17 | Design UI for Admin to Manage accounts | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.11 | PB18 | Design UI for Admin to See user feedback | Phuc, QNhat | Done | 3 | 3 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.12 |  | Design Test case | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.13 | PB01 | Code Frontend for the Admin to Login | QNhat | Done | 4 | 4 | 0 | 3 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.14 | PB02 | Code Frontend for Admin to Logout | Phuc, QNhat | Done | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.15 | PB14 | Code Frontend for Admin to Check Information | Nhat,QNhat | Done | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.16 | PB15 | Code Frontend for Admin to Show dashboard | Nhat | Done | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.17 | PB17 | Code Frontend for Admin to Manage accounts | Nhat, Thai | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
2.18 | PB18 | Code Frontend for Admin to See user feedback | Nhat | Unfinish | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2.19 | PB01 | Code Backend for Admin to Login | Nhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2.2 | PB02 | Code Backend for Admin to Logout | Thai | Done | 4 | 4 | 0 | 5 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
2.21 | PB14 | Code Backend for Admin to Check Information | Nhat | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
2.22 | PB15 | Code Backend for Admin to Show dashboard | Thai | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
2.23 | PB17 | Code Backend for Admin to Manage accounts | Thai | Done | 8 | 8 | 0 | 5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
2.24 | PB18 | Code Backend for Admin to See user feedback | Phuc | Unfinish | 4 | 4 | 0 | 6 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
2.25 |  | Testing | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
2.26 |  | Fix bug | All members | Done | 2 | 2 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
2.27 |  | Re-Testing | All members | Done | 2 | 2 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
2.28 |  | Sprint 2 Review Meeting | All members | Done | 2 | 2 | 0 | 1 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2.29 |  | Release Sprint 2 | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Total | 106 | 106 | 0 | 109 |  | 8 | 4 | 8 | 4 | 1 | 5 | 7 | 4 | 7 | 3 | 7 | 4 | 12 | 5 | 7 | 8 | 8 | 4
|  |  |  | Burn down | [5 empty] | 98 | 94 | 86 | 82 | 81 | 76 | 69 | 65 | 58 | 55 | 48 | 44 | 32 | 27 | 20 | 12 | 4 | 0
|  |  |  | Burn up | [5 empty] | 8 | 12 | 20 | 24 | 25 | 30 | 37 | 41 | 48 | 51 | 58 | 62 | 74 | 79 | 86 | 94 | 102 | 106
[5 empty] | Member | Estimate
[5 empty] | Thai, Bui Son | 29
[5 empty] | Nhat, Nguyen The | 24
[5 empty] | Phuc, Dang Hong | 21
[5 empty] | Nhat, Dao Quang | 21
[5 empty] | Total | 95

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 3 Backlog
Sprint Backlog
[10 empty] | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
3.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 |  | Create Sprint backlog for Sprint 3 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 |  | Create Test Plan document for Sprint 3 | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 |  | Create Database document for Sprint 3 | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | PB01 | Design UI for the shipper to Login | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | PB02 | Design UI for the shipper to Forgot password | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | PB05 | Design UI for Shipper to Change password | Phuc, QNhat | Done | 1 | 1 | 0 | 2 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.8 | PB20 | Design UI for Shipper to View information of customers placing orders | Phuc, QNhat | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9 | PB11 | Design UI for Shipper to receive orders | Phuc, QNhat | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | PB21 | Design UI for Shipper to View personal information | Phuc, QNhat | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11 | PB06 | Design UI for Shipper to View History | Phuc, QNhat | Done | 2 | 2 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12 | PB21 | Design UI for Shipper to Edit personal information | Phuc, QNhat | Done | 2 | 2 | 0 | 5 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13 | PB02 | Design UI for Shipper to Logout | Phuc, QNhat | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14 |  | Design Test case | All members | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15 | PB01 | Code Frontend for the Shipper to Login | Thai | Done | 4 | 4 | 0 | 3 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16 | PB02 | Code Frontend for Shipper to Forgot password | Nhat, Thai | Done | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.18 | PB05 | Code Frontend for Shipper to Change password | Nhat | Done | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.19 | PB20 | Code Frontend for Shipper to View information of customers placing orders | Thai | Done | 2 | 2 | 0 | 3 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | PB11 | Code Frontend for Shipper to receive orders | Thai | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.21 | PB06 | Code Frontend for Shipper to View History | Phuc, QNhat | Unfinish | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.22 | PB21 | Code Frontend for Shipper to Edit personal information | Phuc | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.23 | PB02 | Code Frontend for Shipper to Logout | QNhat | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
3.24 | PB01 | Code Backend for Shipper to Login | Nhat | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
3.25 | PB02 | Code Backend for Shipper to Forgot password | Thai | Done | 4 | 4 | 0 | 5 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
3.26 | PB05 | Code Backend for Shipper to Change password | Thai | Done | 4 | 4 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
3.27 | PB20 | Code Backend for Shipper to View information of customers placing orders | Thai | Done | 4 | 4 | 0 | 6 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
3.28 | PB11 | Code Backend for Shipper to receive orders | Thai | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
3.29 | PB18 | Code Backend for Shipper to View personal information | Thai | Done | 4 | 4 | 0 | 0 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
3.3 | PB06 | Code Backend for Shipper to View History | Nhat | Unfinish | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
3.31 | PB21 | Code Backend for Shipper to Edit personal information | Nhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
3.32 | PB02 | Code Backend for Shipper to Logout | Nhat | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
3.33 |  | Testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
3.34 |  | Fix bug | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
3.35 |  | Re-Testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
3.36 |  | Sprint 2 Review Meeting | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
3.37 |  | Release Sprint 2 | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Total | 120 | 120 | 0 | 127 |  | 8 | 4 | 8 | 4 | 1 | 3 | 4 | 4 | 5 | 10 | 3 | 6 | 7 | 5 | 7 | 10 | 7 | 7 | 10 | 7
|  |  |  | Burn down | [5 empty] | 112 | 108 | 100 | 96 | 95 | 92 | 88 | 84 | 79 | 69 | 66 | 60 | 53 | 48 | 41 | 31 | 24 | 17 | 7 | 0
|  |  |  | Burn up | [5 empty] | 8 | 12 | 20 | 24 | 25 | 28 | 32 | 36 | 41 | 51 | 54 | 60 | 67 | 72 | 79 | 89 | 96 | 103 | 113 | 120
[5 empty] | Member | Estimate
[5 empty] | Thai, Bui Son | 41.75
[5 empty] | Nhat, Nguyen The | 29.75
[5 empty] | Phuc, Dang Hong | 23.25
[5 empty] | Nhat, Dao Quang | 22.25
[5 empty] | Total | 117

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms